## Sheet1
OYO, SOFT PLAY DD COMMENTS- SUBMISSION STAGE 02
1. GENERAL COMMENTS
Date sent |  | Comments | Reply
2020-07-09 |  | A. Does the “Exterior Signage” comply with Kuwait Municipality requirements& regulation specially in absence of Arabic Translation? To be coordinated with TEC Marketing Department. | ON HOLD FOR NEW DESIGN
2020-07-09 |  | B. Does Portal width at main entrance/ Exit comply with KFD requirements& regulation? | DONE AS PER REGULATION
2020-07-09 |  | C. Does KFD will accept to have a tripod turnstile gate at the end of evacuation route? | DONE
2020-07-09 |  | D. Does the Glass type of newly introduced “Evacuation Emergency Exit Door” leading to “Mall Hall” comply with KFD requirements& regulation? | DONE
2020-07-09 |  | E. Soft Play Manufacturer (M/s Cheer Amusement” review and approval on relevant drawings are needed. | DONE
2020-07-19 |  | F. MEPASI Specifications were missing within DD stage Submission. | DONE
2020-07-19 |  | G. Ensue QAQC is done before issuing Final Design Drawings and Documents . | DONE
2020-07-19 |  | H. Coordinate with Tamdeen Mall Management ( TMM) and obtain approval. | After Sign Contract
2020-07-19 |  | I. Prepare and Submit Authorities Approval Drawings include in schedule to obtain the same. Advise Date | During construction
2020-07-19 |  | J. Final Brand Logo data and details to be submitted at Final Design. | ON HOLD FOR NEW DESIGN
2. COMMENTS ON DRAWINGS
Date sent |  | Comments | Status
2020-07-09 |  | 1. Rectify “Project Name” to be “OYOfun” instead of “infunity”, insert TEC logo in all drawing’s template and rectify Revision numbers& dates. | ON HOLD FOR NEW DESIGN
2020-07-09 |  | 2. Replace statement “By Lines” to “By Fit-out Contractor and/or In the Contract” in relevant drawings. | DONE
2020-07-09 |  | 3. In drawing sheets A300 (Electric Points Layout), EP-01 (Power Layout) and ED-01 (Data Layout) kindly add Power& Data points for tripod turnstile gates, also add 5000w Power outlet connection for Compressor. | DONE
2020-07-09 |  | 4. Confirm that 30cm height of Power outlets comply with standard for soft play zones. | DONE; replaced with electrical floor box
2020-07-09 |  | 5. Architectural/ way finding signage are missed. | ON HOLD FOR NEW DESIGN
2020-07-09 |  | 6. In drawing sheet A301, EP-01 (Power Layout) and ED-01 (Data Layout) kindly add Power& Data point at High Level (Ceiling Level) for projector on “Ball Pool” zone. | DONE
2020-07-09 |  | 7. In drawing sheet A400 (Finishes Layout) add Table of Finishes. | DONE
2020-07-09 |  | 8. In drawing sheet A510 (sections) for section-01b; the shown Light Fixtures aren’t comply/ match with Light fittings shown in both Architectural drawing A200 and Electrical drawing sheet EL-01 (Light Layout). | DONE
2020-07-09 |  | 9. In Electrical drawing sheet EL-01 (Light Layout) is it possible that Light Fixture L07 (LED strip Light) to be LED Tube Light. | DONE
2020-07-09 |  | 10. Add illuminated directional Exit Signs (currently only 3 numbers of Exit Sign at Exit doors). | DONE
2020-07-09 |  | 11. Is there DMX Light Fixtures and control? | NO
2020-07-09 |  | 12. Is there Sound System in-addition to Public Address System? | YES
2020-07-09 |  | 13. In drawing sheet ED-02 (CCTV Layout) is there security camera inside “Candy Bus”? | No need; small internal space
2020-07-09 |  | 14. In drawing sheet EP-01 (Power layout) define location of “Main Switch Board Panel)? Is it possible to have MSB at Main entrance right hand side, as well as “Fire Alarm Panel”? | NOT APPLICABLE
2020-07-09 |  | 15. In drawing sheet AC-100, Revisit duct sizes and draw cross section under drop beam along grid (2r). | Refer to arch drawing A-200
2020-07-09 |  | 16. Condensation drainpipes and Refrigerant pipelines for DSU (Duct-able Split Units) are missed.
2020-07-09 |  | 17. Legend is missed on drawing sheet FF-01 (Firefighting Layout). | DONE
2020-07-09 |  | 18. Referred to List of drawing sheet A-001, Drawing sheet FF-100 is missed. | DONE
2020-07-19 |  | 19. Drawings are wrongly titled as Schematic Design instead of Design Development . Resubmit corrected drawings . | DONE
2020-07-19 |  | 20. Provide Game Equipment schedule with MEP requirements after coordinating with cheers . | DONE
2020-07-19 | 21. A-100 & A-101 Construction Layouts:
2020-07-19 |  | • Grid are missing on plans | No need, it is fit-out project in existing shop
2020-07-19 |  | • Equipment to be located with reference to grid and Work Point ( WP ) to be established for each game equipment. | No need, it is fit-out project in existing shop
2020-07-19 |  | • Include Perspective and images as denoted on the plans – All material tags to be shown on Perspectives too. | DONE
2020-07-19 |  | • Indicate the levels in meters corresponding to the finish floor level for both A-100 and A-101 | DONE
2020-07-19 |  | 22. A-200 RCP- Shop Front Signage and Lighting missing to shown on RCPS | DONE
2020-07-19 |  | 23. A- 300 , A-301 Electrical Points Layout- Provide dimension and Locate the electrical points | DONE
2020-07-19 |  | 24. A-400 Finishes layout- Include Change of finish (COF) interface details at Wall, Floor and Ceiling | DONE
2020-07-19 |  | 25. A-450- Furniture Legends Missing | DONE
2020-07-19 |  | 26. A-501- Shop Front Signage – English and Arabic Missing | ON HOLD FOR NEW DESIGN
2020-07-19 |  | 27. A-510 to A-514 Sections- Material Tags missing | DONE
2020-07-19 |  | 28. A- 810 Counter Detail- Material, finishes, Construction and fixation details missing . | In contractor shop drawings
2020-07-19 |  | 29. A-820 to 828 Furniture Details- Materials tag, Finishes, construction and fixation details missing | DONE
2020-07-19 |  | 30. A- 830 , A- 831- Material Details ,Finish and Technical Data missing | DONE
2020-07-19 |  | 31. A-901 Signage Detail- Update with revised Signage as per TEC Brand requirements | ON HOLD FOR NEW DESIGN
2020-07-19 |  | 32. A-920 Door Schedule • Province Door Hardware Set Details , • Door Glazing to be laminated and Glazing thickness to be as per Code Requirements . • Confirm if the door is a frameless door . | DONE
3. COMMENTS ON SPECIFICATIONS
Date sent |  | Comments | Status
2020-07-09 |  | A. On Page6, As per Manufacturer "3D Design Concept" Piano matt finishing is ended before Emergency Evacuation Door, but the current status create obstruction in evacuate route as well as such obstruction on evacuate route to the Emergency Exit door having high risk of KFD rejection. | KFD approvals will be provided during construction, and it is our responsipality
2020-07-09 |  | B. On pages 22 till 31; housing of Light Fixtures are wooden. Is it Approved from KFD? Is it of lower cost compared to Aluminum of wooden shape? | KFD approvals will be provided during construction, and it is our responsipality
2020-07-09 |  | C. Glass types on pages 37&38 of 10mm tempered glass and Section-08800 (Glass and Glazing), Is it possible to be Single laminated tempered low lead clear glass (6mm+PVA+6mm) for windows considering Sound Transmission permissible limits. | DONE
2020-07-09 |  | D. On Pages 49& 50 the decorative fence material are “Powder Coated Meatal Structure”, Is it possible to be “Aluminum Powder Coated” for neat& better manufacturing. | We can handle with metal material
2020-07-09 |  | E. On Page 53 GRP proposed material for such fence is of huge cost, Is it possible to be “Powder Coated Steel fencing” of less cost. | It is including our Price padget, and it is near to kids we can`t make it metal
2020-07-09 |  | F. On section 09900-Painting, Is it possible to limit Manufacture Product of equal brands to both “Jotun-Kuwait and Hempel-UAE” only without others “Sigma-KSA and GTC-Kuwait”. | DONE
2020-07-09 |  | G. All MEP specification’s divisions are missed. | DONE
2020-07-19 |  | H. Incomplete CSI format , Doc III -2 Specification provided : Material data , Manufacture Name and Origin /Sources Missing | DONE
2020-07-19 |  | I. Incomplete Doc III -2 Specification , Material Selection Provided for the following finishes : Performance material Data - Thickness , composition ,properties RAL color … Manufacture Name and Origin /Sources , but not limited to are missing • Floor – F-01 , F-02 • Wall – W-01 , W-02,W-03,W-04 and W-05 • Ceiling – C-01 ,C-02 • Lighting Selection – Technical Data, Manufacture Name and Origin /Sources Missing • Glass Type – Glass to be laminated & safety tempered type -Thickness to be specified, Lateral Load ( Impact load ) to be mentioned as per codes and standard, Structural design calculation for Glazing to be provided . • Metal Type – MT-01, MT-02 and MT-03 – Thickness, Finish, Color ( RAL No.), Paint type missing • Art work – Details are missing • Furniture – Details are missing | DONE, AS PER SAMPLE BOARD
2020-07-09 |  | 4. LINES is advised to revisit Doc.-I and Doc.-II and Doc.-III Div.-1 with close coordination with TSC.
5.BOQ
Date sent |  | Comments | Status
2020-07-09 |  | A. On Division-8 all windows are missed. | DONE
2020-07-09 |  | B. On Division-9, Item III-4/9-1 (A&B) Please elaborate meaning of (White Screed)?
6. M/s Lines Design Development Stage Cost Estimate
Date sent |  | Comments | Status
2020-07-09 |  | A. It was agreed during High Management Meeting, conducted on April 21st 2020, that the price is negotiated with Lines and to provide a BID (price) for execution the works after completion of final design. Meanwhile, Not all the items are quoted in Division-16 Electr. Lines Updated Estimated Cost (submitted last Tuesday 30-6-2020) of total Estimated cost of KD 103,208.500 excluding Contingencies, Insurance Policies rather than Budgetary Cost (addressed to TSC on Handing Over mail dated 30-10-2019) of amount KD80,000 excluding Contingencies of KD5,600. TSC justification is needed for Budgetary Cost deviation. | Our budget 103,208.500KD was approved by the top managmentduring the meeting held on 19/7/2020
6. Control Sample Board related Comments
Date sent |  | Comments | Status
2020-07-19 |  | A. Incomplete control samples board submitted by LINES , Resubmit after complying with comments : • The Material sample board shown to Tamdeen High Management ( THM) today was not tagged as per DD Stage Material Key Note, Product Manufacture name and County of Origin is missing .The images for the revised sample board to be submitted to TEC/TSC as part of final Design Submission for information and Record. Reissue final control sample board for THM approval and Sign-off . | DONE
MEP COMMENTS
Date sent |  | Comments | Status
2020-07-18 |  | A. ELECTRICAL
2020-07-18 |  | 1. Find on the PDF’s and xl files attached having the comments related to electrical.
General Comments
|  | Provide list of equipments indicating the required electrical loads. | DONE
|  | Single line diagrams(SLD) to be provided for electrical and ELV, indicating available services and further distribution. Scope of works of this contract to be clearly identified in the SLD | DONE
|  | Small power provided in layout is not reviewed. This will be reviewed in DD when the list of equipment with electrical load is provided. | NOTED
|  | Ensure Electrical panels and IT racks could be accessed only by the maintenance staff. | NOTED
|  | Refer to drawings attached | DONE
|  | Lighting calculations to be provided in DD to ensure level of lighting. | Under Progress
|  | Field of view of camera to be provided in DD to ensure coverage. | DONE
|  | Could not locate voice evacuation speakers in the layout. Speaker for voice evacuation and public address to be clearly identified in layout in DD. | DONE
Service Design Criteria
|  | Latest MOI requirements to be considered | NOTED
|  | Recording to be 120days as per MOI. | NOTED
| EL-01-EL-01 | Specification of all light types with the required datasheets to be provided | Under Progress
|  | Installation details of all special lights to be provided | In contractor shop drawings
|  | Lighting calculations to be provided. | Under Progress
|  | Emergency lights specifications to be provided. | DONE
|  | Lighting layout for level 2 to be included. | The place is only one floor
|  | EXIT lighting location to be restudied | DONE, refer to Arch. Dwgs
|  | Power for GRP element with inner light (U-25 and U26) missing | DONE
|  | Light for Candy bus to be indicated | As per Game Supplier
|  | Some areas does not have proper coverage. lighting calculation to be provided | Under Progress
|  | Power for Custome made light fitting (U-11) missing | Under Progress
|  | Required elevations to be provided for the entrance incorporating LED lights. | Refer to Arch. Dwgs
|  | Ample emergency lights to be provided at entrance | DONE
|  | Power for LED light inside the acrylic box in Graphic tree. (U3) | Under Progress
| EP-01,EP-02-EP-01 | Provide list of equipments indicating the required electrical loads. | DONE
|  | Single line diagrams(SLD) to be provided for electrical and ELV, indicating available services and further distribution. Scope of works of this contract to be clearly identified in the SLD | DONE
|  | All equipments to which power is provided to be identified | DONE
|  | power for screen to be indicated in layout and included in the schedule of points | DONE
| EP-01,EP-02-EP-02 | Equipment schedule to be provided clearly indicating the power requirements. These drawings will be reviewed in detail upon receipt of the schedule | DONE
|  | Details of all equipments to be added in schedule | DONE
|  | Why do we have three sections in DB? Study possibility of providing isolator with earthleakage for all AHUs | NOTED
|  | 300mA to be considered for lighting section | DONE
| FA-01-FA-0-1 | Detector above ceiling to be located in layout | DONE
|  | Additional breakglass to be considered as required | DONE
|  | Ensure that all new devices can be accomodated in the existing FACP. | DONE
| ED-01-ED-01 | Equipment schedule to be provided clearly indicating the data requirements. These drawings will be reviewed in detail upon receipt of the schedule | DONE
|  | Standard legend to be used for data outlets | DONE
|  | All equipments to which data is provided to be identified | DONE
|  | Where is the location of Knet. Provide required power/data | DONE
|  | Printer location to be indicated in layout | DONE
|  | Only empty conduits are available for IT. Location to be identified in layout and extension upto the rack location to be indicated with the required drawwire. | DONE
| ED-02-ED-02 | CCTV and WAP coverage to be marked in the layout. | DONE
|  | Where will be the CCTV monitored? | DONE
|  | Entry and exit to be monitored. | DONE
| ED-02-ED-03 | Only empty conduits are available in the fllor. Contractor to extend it upto the rack location(through ceiling) with the required draw wire | DONE
| SPECIFICATIONS | Electrical and ELV specifications to be provided | DONE
2020-07-18 |  | B. HVAC:-
2020-07-18 |  | 1. The cost is reduced to be 15,000 KD (confirm that the same is including electric works for HVAC units, builder works for HVAC) | The total lump sum cost was approved from top management
2020-07-18 |  | 2. Show the refrigeration pipe routing and condensing units on roof | DONE
2020-07-18 |  | 3. The DX condensing units to be with factory epoxy coated condenser fines | DONE
2020-07-18 |  | C. FIREFIGHTING :-
2020-07-18 |  | 1. Show the existing piping works and the new piping works, use the existing piping/sprinkler as required. | We changed the piping route regarding the game structure heights
2020-07-18 |  | 2. Confirm that the sprinkler shall be only upright and the ceiling is more than 70% opened | CONFIRMED
2020-07-18 |  | 3. Add KFD approval for as built to the contractor scope of works. | DONE
2020-07-18 |  | D. BILL OF QUANTITIES :-
2020-07-18 |  | Find BOQ comments related to Civil / Architectural works:
2020-07-18 |  | 1. Specification Section numbers to be mentioned in BOQ as heading in all divisions. | NOTED
2020-07-18 |  | 2. Please clarify requirement of below item. | The total lump sum cost was approved from top management, and the measurements method could be by unit.